## Agile Sprint Backlog - BLANK
SPRINT 2 BACKLOG AND BURNDOWN CHART
BACKLOG TASK | ORIGINAL ESTIMATE | ASSIGNED TO | PRIORITY | TAG | STATUS | STORY POINTS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1: As a user, I would like to order the results by distance, so I can find out which hospital is closest to me. |  |  | 9 | High | Completed
Task: Find out how to Calculate distance from user to hospitals. | 2 | Arran Roy | 9 | High | Completed | 2 | 1 | 0 | 0 | 0 | 0
Task: Taking the results of hospitals and working out each distance. | 4 | Arran Roy, Kyle Leggate | 9 | High | Completed | 4 | 4 | 4 | 2 | 0 | 0
Task: Sort results by distance (ascending) | 1 | Melvin Binu | 6 | High | Completed | 1 | 1 | 1 | 0.5 | 0 | 0
Task: Draw a line for the route to a hospital from user location on the map. | 1 | Arran Roy | 4 | Moderate | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task: Integrate all functions of the user story into the main program | 3 | Arran Roy, Kyle Leggate, Melvin Binu | 9 | High | Completed | 3 | 3 | 3 | 3 | 2 | 0
User Story #2: As a User, I want to be able to set the distance range before searching, so I can set a minimum and maximum distance from myself. |  |  | 5 | High | Completed
Task: Implement range feature for distance. | 1 | Kyle Leggate | 7 | High | Completed | 1 | 1 | 1 | 1 | 0 | 0
Task: Integrate range features into the main program | 1 | Kyle Leggate | 7 | High | Completed | 1 | 1 | 1 | 1 | 0.5 | 0
User Story #3: As a user, I would like the UI to be easier to navigate and information to be displayed more clearly |  |  | 5 | Moderate | Completed
Task: Redesign UI into 3 different windows/ tabs. | 1 | Lin Baosong | 5 | Moderate | Completed | 1 | 0.83 | 0.5 | 0 | 0 | 0
Task: Spike - Research best way to display results vs a listbox. | 2 | Kyle Leggate | 5 | Moderate | Completed | 2 | 0 | 0 | 0 | 0 | 0
Task: Spike - Research how to let the user to select something from a list of results | 1 | Kyle Leggate | 5 | Moderate | Completed | 1 | 1 | 0 | 0 | 0 | 0
User Story #4: As a user, I want to be able to search for places with certain procedures using the procedure name, so I don't have to remember the procedure code. |  |  | 5 | Moderate | Completed
Task: Take in user input of procedure description. | 1 | Paul Ritch | 7 | HIgh | Completed | 1 | 1 | 1 | 1 | 1 | 0
Task: Display results based on procedure keywords according to dataset. | 2 | Paul Ritch | 7 | High | Completed | 4 | 3 | 2 | 0 | 0 | 0
Task: Display results based on layman's terms for the procedure. | 5 | Paul Ritch | 5 | Moderate | Completed | 2 | 2 | 2 | 2 | 0 | 0
Task: Integrate the functions of the user story into the main program | 1 | Paul Ritch, Kyle Leggate | 7 | High | Completed | 1 | 1 | 1 | 1 | 1 | 0
User Story #5: As a User, I want to be able to use my live location so I can find the nearest hospital from my current position. |  |  | 4 | Low, Epic | Completed
Task: Spike - research methods of implementing live location | 1 | Melvin Binu | 3 | Low | Completed | 1 | 0 | 0 | 0 | 0 | 0
Task: Implement live location | 2 | Melvin Binu | 3 | Low | Completed | 2 | 2 | 1 | 0.5 | 0.25 | 0
User Story #6: As a user, I want the Map position placeholders to show price so I can easily see how much the procedure will cost at a hospital. |  |  | 2 | Low | Partially Complete
Task: Add map position placeholders for each hospital. | 2 | Arran Roy | 7 | High | Completed | 2 | 2 | 2 | 0 | 0 | 0
Task: Display price on the hospital map placeholders. | 1 | Arran Roy | 4 | Moderate | Not Started | 1 | 1 | 1 | 1 | 1 | 1
Task: Integrate the functions of the user story into the main program | 1 | Arran Roy | 7 | High | Partially Complete | 1 | 1 | 1 | 1 | 0.5 | 0.25
User Story #11: As a user with disabilities, I would want the software to be easy and accessible for myself to use. |  |  | 3 | Low, Optional | Completed
Task: Accessiblity - options to change font size, font colours, increase size of objects in UI. | 3 | Jason Khan | 3 | Low | Completed | 3 | 1 | 0 | 0 | 0 | 0
Task: Continuous Integration | 6 | Jason Khan | 3 | Low | Completed | 3 | 3 | 3 | 0 | 0 | 0
Task: Approve/Finalise UI features | 2 | Jason Khan | 3 | Low | Completed | 2 | 2 | 2 | 2 | 0 | 0
Task: Review pull requests and approve/finalise integration | 1 | Jason Khan | 9 | High | Completed | 1 | 1 | 1 | 1 | 0.5 | 0
TOTAL | [5 empty] | 41 | 33.83 | 27.5 | 17 | 6.75 | 1.25