## Agile Sprint Backlog - BLANK
SPRINT 2 BACKLOG AND BURNDOWN CHART
BACKLOG TASK | ORIGINAL ESTIMATE | ASSIGNED TO | PRIORITY | TAG | STATUS | STORY POINTS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1: As a user, I would like to order the results by distance, so I can find out which hospital is closest to me. |  |  | 9 | High | In Progress
Task: Find out how to Calculate distance from user to hospitals. | 2 | Arran Roy | 9 | High | Completed | 2 | 1 | 0
Task: Taking the results of hospitals and working out each distance. | 4 | Arran Roy, Kyle Leggate | 9 | High | Not started | 4 | 4 | 4
Task: Sort results by distance (ascending) | 1 | Melvin Binu | 6 | High | Not started | 1 | 1 | 1
Task: Draw a line for the route to a hospital from user location on the map. | 1 | Arran Roy | 4 | Moderate | Completed | 1 | 1 | 0
User Story #2: As a User, I want to be able to set the distance range before searching, so I can set a minimum and maximum distance from myself. |  |  | 5 | High | Not started
Task: Implement range feature for distance. | 1 | Kyle Leggate | 7 | High | Not started | 1 | 1 | 1
User Story #3: As a user, I would like the UI to be easier to navigate and information to be displayed more clearly |  |  | 5 | Moderate | In Progress
Task: Redesign UI into 3 different windows/ tabs. | 1 | Lin Baosong | 5 | Moderate | In Progress | 1 | 0.83 | 0.5
Task: Spike - Research best way to display results vs a listbox. | 2 | Kyle Leggate | 5 | Moderate | Completed | 2 | 0 | 0
User Story #4: As a user, I want to be able to search for places with certain procedures using the procedure name, so I don't have to remember the procedure code. |  |  | 5 | Moderate | In Progress
Task: Take in user input of procedure description. | 1 | Paul Ritch | 7 | HIgh | Not Started | 1 | 1 | 1
Task: Display results based on procedure keywords according to dataset. | 2 | Paul Ritch | 7 | High | Completed | 2 | 1 | 0
Task: Display results based on layman's terms for the procedure. | 5 | Paul Ritch | 5 | Moderate | Not Started | 5 | 5 | 5
User Story #5: As a User, I want to be able to use my live location so I can find the nearest hospital from my current position. |  |  | 4 | Low, Epic | In Progress
Task: Spike - research methods of implementing live location | 1 | Melvin Binu | 3 | Low | Completed | 1 | 0 | 0
Task: Implement live location | 2 | Melvin Binu | 3 | Low | In Progress | 2 | 2 | 1
User Story #6: As a user, I want the Map position placeholders to show price so I can easily see how much the procedure will cost at a hospital. |  |  | 2 | Low | Not Started
Task: Add map position placeholders for each hospital. | 2 | Arran Roy | 7 | High | Not Started | 2 | 2 | 2
Task: Display price on the hospital map placeholders. | 1 | Arran Roy | 4 | Moderate | Not Started | 1 | 1 | 1
User Story #7: As a developer, I want to be able to edit data in data set so information can be up to date. |  |  | 1 | Low, Optional | Not Started
User Story #8: As a developer, I want to be able to add new data to data set so more information can be used. |  |  | 1 | Low, Optional | Not Started
User Story #9: As a developer, I want the results displayed to take into account the users past activity. |  |  | 1 | Low, Optional | Not Started
User Story #10: As a developer I want to be able to delete data from the data set in case it is redundant. |  |  | 1 | Low, Optional | Not Started
User Story #11: As a user with disabilities, I would want the software to be easy and accessible for myself to use. |  |  | 3 | Low, Optional | In Progress
Task: Accessiblity - options to change font size, font colours, increase size of objects in UI. | 3 | Jason Khan | 3 | Low | Completed | 3 | 1 | 0
Task: Continuous Integration | 6 | Jason Khan | 3 | Low | Not Started | 6 | 6 | 6
TOTAL | [5 empty] | 35 | 27.83 | 22.5 | 0 | 0 | 0 | 0