## Sheet1
Description | Estimate | Priority | Label | Other
Accessibility | N/A | N/A |  | Optional
People can search for places with certain procedures using the procedure code. | 1 | 8 | Major
Results can be ordered by price. | 1 | 7 | Major
Calculate distance from user to hospitals. | 7 | 7 | Major
User inputted location is used. | 2 | 7 | Major
Spike team - research map integration | 7 | 6 | Moderate
Results can be ordered by distance. | 1 | 6 | Major
User can set price range before search. | 3 | 6 | Major
User can set distance range before search. | 8 | 5 | Moderate
People can search for places with certain procedures using the procedure name. | 4 | 5 | Moderate
Windows form design UI | 3 | 5 | Moderate
Users live location is used. | 30 | 4 | Moderate | EPIC
Positioning of output should be displayed on a map. | 20 | 4 | Moderate | EPIC
Design desktop UI form | 4 | 3 | Low
Users can set their own custom ranking. | 3 | 2 | Low | Optional
Map position placeholders should show price. | 3 | 2 | Low
As a developer, i want the results displayed to take into account the users past activity. | 6 | 1 | Low | Optional
Data in data set can be edited. | 2 | 1 | Low | Optional
New data can be added to data set. | 2 | 1 | Low | Optional
Data can be deleted from data set. | 2 | 1 | Low | Optional
Design Logo/brand for application | 1 | 1 | Low