## Sheet1
Description | Estimate | Priority | Label | Other | Assigned To
People can search for places with certain procedures using the procedure code. | 4 | 8 | Major |  | Paul Ritch
Results can be ordered by price. | 2 | 7 | Major |  | Melvin Binu
Calculate distance from user to hospitals. | 4 | 7 | Major |  | Arran Roy
Spike team - research map integration | 7 | 6 | Moderate |  | Arran Roy
User inputted location is used. | 2 | 7 | Major |  | Jason Khan
Results can be ordered by distance. | 2 | 6 | Major |  | Melvin Binu
User can set price range before search. | 3 | 6 | Major |  | Kyle Leggate
User can set distance range before search. | 8 | 5 | Moderate |  | Kyle Leggate
People can search for places with certain procedures using the procedure name. | 20 | 5 | Moderate |  | Paul Ritch
Windows form design UI | 3 | 5 | Moderate |  | Baosong Lin
Positioning of output should be displayed on a map. | 15 | 4 | Moderate | EPIC | Arran Roy
Map position placeholders should show price. | 3 | 2 | Low |  | Unassigned
Design desktop UI form | 4 | 3 | Low |  | Baosong Lin
Design Logo/brand for application | 1 | 1 | Low |  | Baosong Lin