## Agile Sprint Backlog - BLANK
SPRINT BACKLOG AND BURNDOWN CHART
BACKLOG TASK | PRIORITY | TAG | ASSIGNED TO | ORIGINAL ESTIMATE | STORY POINTS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
People can search for places with certain procedures using the procedure code. | 8 | High | Paul Ritch | 1 | 4 | 3 | 1 | 0 | 0 | 0
Results can be ordered by price. | 7 | High | Melvin Binu | 1 | 3 | 2 | 1 | 0 | 0 | 0
User inputted location is used. | 7 | High | Jason Khan | 2 | 6 | 5 | 4 | 2 | 0 | 0
Spike team - research map integration | 6 | Moderate | Arran Roy | 7 | 3 | 1 | 0 | 0 | 0 | 0
User can set price range before search. | 6 | High | Kyle Leggate | 3 | 3 | 2 | 1 | 0 | 0 | 0
User can set distance range before search. | 5 | Moderate | Kyle Leggate | 8 | 3 | 2 | 1 | 0 | 0 | 0
Windows form design UI | 4 | Moderate | Lin Baosong | 2 | 2 | 0 | 0 | 0 | 0 | 0
Design desktop UI form | 4 | Low | Lin Baosong | 1 | 1 | 0 | 0 | 0 | 0 | 0
Results can be ordered by distance. | 6 | High | Melvin Binu | 1 | 3 | 2 | 1 | 0 | 0 | 0
People can search for places with certain procedures using the procedure name. | 5 | Moderate | Paul Ritch | 4 | 20 | 20 | 20 | 19 | 17 | 17
Positioning of output should be displayed on a map. | 4 | Epic | Arran Roy | 20 | 8 | 0 | 5 | 2 | 0 | 0
Design Logo/brand for application | 2 | Low | Lin Baosong | 3 | 3 | 0 | 0 | 2.5 | 0 | 0
TOTAL |  |  |  |  | 59 | 37 | 34 | 25.5 | 17 | 17